## Integrating Climate Resilience into Construction Project Management: A Narrative Review of Frameworks, Policies, and Implementation Challenges

### Abstract

Climate change increases the risk of floods, heatwaves, droughts, and sea-level rise for infrastructure investments. These dangers disrupt supplies, delay schedules, and raise prices, demonstrating that standard Construction Project Management (CPM)—focused on cost, scope, and time—must include climate resilience. This narrative study summarizes worldwide frameworks, policy instruments, and CPM climate resilience implementation issues. A structured literature search was conducted on Scopus, Web of Science, ScienceDirect, and Google Scholar using “climate resilience,” “construction project management,” “infrastructure adaptation,” and “policy integration.” Thematic analysis identified conceptual frameworks, governance mechanisms, and practice barriers from 2000 to 2025. Four main ideas developed. First, resilience frameworks like the Sendai Framework, IPCC AR6 Pathways, ISO 14090/14091, World Bank CSIF, and FIDIC advice support risk-informed and adaptive project management. Second, insufficient enforcement, fragmented mandates, and no resilience KPIs remain policy deficiencies. Financial disincentives, insufficient climatic data, and uneven human capabilities impede implementation. Finally, developing best practices suggest lifecycle alignment, digital integration (BIM–GIS–twins), nature-based solutions, and outcome-based procurement. Changing project success to focus on continuity, recovery, and adaptation is needed to include resilience into CPM. Resilience thinking throughout project lifecycles, procurement standards, funding methods, and professional education can help the construction sector move from reactive hardening to proactive, climate-informed infrastructure delivery.

## 1. Introduction

### 1.1 Background and Rationale

Climate resilience is the ability of systems, communities, and infrastructure to foresee, prepare for, and recover from climate shocks while sustaining vital functions. Resilience in construction means buildings, roads, bridges, and related facilities can withstand, adapt to, and recover from extreme weather. However, Construction Project Management (CPM) uses the “triple constraint” of cost, scope, and time to plan, coordinate, and control a project from start to finish. Project success depends on these criteria, but climate change is revealing that efficiency-optimized projects are often unprepared for climate-induced interruptions[1].

Floods, heatwaves, droughts, and sea-level rise disrupt supply systems, damage materials, and delay construction projects worldwide. Extreme rain can undermine foundations and substructures, while heat stress diminishes labor productivity and concrete curing. These risks increase project costs and endanger infrastructure and public safety. As these risks become more apparent, project management must shift to climate-informed, resilience-based methods.
Thus, CPM must incorporate climate resilience for sustainable, durable, and climate-proof infrastructure. Project managers can anticipate risks, design adaptive strategies, and preserve infrastructure assets. Integration facilitates the worldwide shift to low-carbon, risk-informed development and international sustainability goals. Resilience in the project lifecycle turns reactive project management into proactive, protecting investments from climate change[2].

### 1.2 Research Gap

There is no synthesis on how resilience principles are integrated into building project management despite growing climate adaption research. Many resilience integration studies ignore management, policy, and institutional aspects in favor of engineering or architectural answers such materials innovation, green building design, and structural retrofitting. Thus, the relationship between project management and climate adaptation is poorly understood. This review fills that gap by unifying information and suggesting practical ways to integrate theory, policy, and implementation.

### 1.3 Aim and Objectives

Aim: To review and synthesize existing frameworks, policies, and implementation challenges related to integrating climate resilience into construction project management.

Objectives:

- Identify and describe major frameworks guiding climate-resilient construction.

- Examine global and regional policy instruments that shape resilience integration.

- Analyze practical challenges and barriers faced during implementation.

- Recommend pathways for strengthening resilience within project management practices.

### 1.4 Significance of the Review

Academic discourse is linked to policy relevance and project delivery in this review. It promotes SDGs 9, 11, and 13 on resilient infrastructure, sustainable cities, and climate action. Synthesizing fragmented literature, the paper provides a conceptual foundation for practitioners, educators, and policymakers to embed climate resilience into construction project management frameworks to improve sustainability and adaptive capacity in the built environment.

## 2. Methodology

### 2.1 Narrative Review Design

A narrative review was used to synthesize climate resilience and building project management literature. Because environmental science, engineering, project management, and governance are interrelated and policy-driven, this method was chosen. Unlike systematic reviews with rigid inclusion protocols and quantitative meta-analysis, narrative reviews can qualitatively synthesize conceptual frameworks, policy instruments, and practice-based experiences across disciplines. This flexibility allows the inclusion of gray literature, institutional reports, and global policy documents, which are essential to resilience integration but generally excluded from systematic assessments. The method provides a holistic view of how construction management frames, operationalizes, and challenges climate resilience concepts.

### 2.2 Literature Search

A controlled but flexible literature search was conducted in four major academic databases—Scopus, Web of Science, ScienceDirect, and Google Scholar—to cover academic and professional sources. The search included “climate resilience,” “construction project management,” “infrastructure adaptation,” “resilient frameworks,” and “policy integration.” Results were refined using Boolean operators (“AND,” “OR”). The timeline was constrained to January 2000–September 2025 to reflect climate resilience and project management improvements since the Kyoto Protocol, Paris Agreement, and Sendai Framework. Key article reference lists were also examined for additional relevant publications.

### 2.3 Inclusion and Exclusion Criteria

Peer-reviewed journal publications, institutional reports, policy briefs, and framework documents on building, infrastructure resilience, or climate adaption management were reviewed. Studies that were authored in languages other than English, focused on unrelated sectors like agriculture or health, or explored climate change consequences without tying them to project management or infrastructure contexts were removed. This kept the review on climate resilience integrated management, policy, and strategy.

### 3.4 Data Synthesis

Extracted data were analyzed through thematic synthesis. Each source was reviewed to identify recurring patterns, conceptual models, and policy linkages. The findings were organized into three major thematic clusters:

- Conceptual and Framework-based Insights – understanding theoretical underpinnings and resilience models.

- Policy and Governance Dimensions – exploring institutional mechanisms and regulatory instruments.

- Implementation and Practice Barriers – identifying constraints, knowledge gaps, and enabling factors for integrating resilience into construction project management.

This structured thematic organization provided a coherent framework for discussing findings in subsequent sections.

### 3.1 Narrative Review Design

A narrative review was used to synthesize climate resilience and building project management literature. Because environmental science, engineering, project management, and governance are interrelated and policy-driven, this method was chosen. Unlike systematic reviews with rigid inclusion protocols and quantitative meta-analysis, narrative reviews can qualitatively synthesize conceptual frameworks, policy instruments, and practice-based experiences across disciplines. This flexibility allows the inclusion of gray literature, institutional reports, and global policy documents, which are essential to resilience integration but generally excluded from systematic assessments. The method provides a holistic view of how construction management frames, operationalizes, and challenges climate resilience concepts.

### 3.2 Literature Search

A controlled but flexible literature search was conducted in four major academic databases—Scopus, Web of Science, ScienceDirect, and Google Scholar—to cover academic and professional sources. The search included “climate resilience,” “construction project management,” “infrastructure adaptation,” “resilient frameworks,” and “policy integration.” Results were refined using Boolean operators (“AND,” “OR”). The timeline was constrained to January 2000–September 2025 to reflect climate resilience and project management improvements since the Kyoto Protocol, Paris Agreement, and Sendai Framework. Key article reference lists were also examined for additional relevant publications.

### 3.3 Inclusion and Exclusion Criteria

Peer-reviewed journal publications, institutional reports, policy briefs, and framework documents on building, infrastructure resilience, or climate adaption management were reviewed. Studies that were authored in languages other than English, focused on unrelated sectors like agriculture or health, or explored climate change consequences without tying them to project management or infrastructure contexts were removed. This kept the review on climate resilience integrated management, policy, and strategy.

### 3.4 Data Synthesis

Extracted data were analyzed through thematic synthesis. Each source was reviewed to identify recurring patterns, conceptual models, and policy linkages. The findings were organized into three major thematic clusters:

- Conceptual and Framework-based Insights – understanding theoretical underpinnings and resilience models.

- Policy and Governance Dimensions – exploring institutional mechanisms and regulatory instruments.

- Implementation and Practice Barriers – identifying constraints, knowledge gaps, and enabling factors for integrating resilience into construction project management.

This structured thematic organization provided a coherent framework for discussing findings in subsequent sections.

4. Conceptual Foundations: Climate Resilience in Construction

4.1 Defining Climate Resilience

“Climate resilience” evolved from “climate adaptation.” Elevating equipment and upsizing drains were examples of climate adaptation. Resilience means assets, organizations, and communities can anticipate, absorb, recover from, and adapt to climatic shocks and long-term pressures while maintaining service levels. Its meaning comes from two complementary traditions. Ecological resilience prioritizes diversity, redundancy, and rearrangement to absorb disturbance without changing qualitatively. Engineering resilience prioritizes robustness, dependability, and control to speed up system recovery after a disturbance. Ecological principles influence landscape-scale and nature-based hazard-reduction strategies (e.g., riparian buffers, green roofs), while engineering principles guide asset-level performance. In this view, resilience is a performance attribute that must be specified, procured, tested, and monitored throughout the project[3].

## 4.2 The Construction Project Life Cycle Perspective

The standard project life cycle phases work best for embedding resilience: 
• Initiation: Conduct an early climate risk screen to identify risks (heat, flood, wind, fire, sea-level rise, drought) and exposure pathways. In the project charter and business case, define resilience outcomes (e.g., maximum downtime, safety thresholds) and use scenario-based assumptions. Site selection, land-use compatibility, and criticality rating matter now.
• Planning: Translate dangers into adaptive design and acceptability criteria. Whole-life costing can analyze staged (pathway) options, and specify green, durable materials for non-stationary conditions. Integrate hazard layers into BIM–GIS models to assess drainage, shading, alignment, and emergency access. Create weather-aware schedules with seasonal buffers and resilience KPIs in the quality plan[4]. 

• Manage construction in varying climates. Real-time monitoring (e.g., river levels, heat index, wind alerts) can trigger technique adjustments, temporary works protection, or resequencing. Ensure worker wellness (heat/air-quality protocols), supply chain security (essential spares, alternate routes), and change decision learning. Contracts should specify extreme-weather delays and monitoring data sharing. 
• Closure: Test resilience by commissioning under stress conditions (e.g., floodgate operation, backup power switchover). Provide an adaptable digital twin with hazard layers, trigger thresholds, and O&M procedures. Learn what succeeded, what failed, and which triggers or thresholds need adjusting to improve resilience in future initiatives[5].

A visual summary of resilience integration across project phases is shown in Figure 1, highlighting how key inputs (hazards and climate scenarios), tools (BIM–GIS, stress tests), and outputs (resilience requirements, KPIs, commissioning tests, and lessons learned) align throughout the lifecycle to support adaptive management.

Figure 1. Resilience Integration Points in the Construction Project Lifecycle. Diagram showing how climate resilience is embedded across project phases—linking inputs (hazards, scenarios), tools (BIM–GIS, stress tests), and outputs (requirements, KPIs, commissioning tests) within a continuous adaptive management cycle.

## 4.3 Systems Thinking and the Resilience Lens

Construction projects are socio-technical systems integrated in utilities, transport, supply chains, ecosystems, finance, and communities. Under climate change, these networks are complex adaptive systems with feedbacks, thresholds, and emergent behavior, thus linear, single-hazard assumptions are inappropriate. Systems thinking redefines success from “build to spec” to “sustain function under stress.” Following are three resilience-design traits: 
• Flexible designs: Adaptable to changing hazards (e.g., foundations ready for floodwall raising, roof structures pre-engineered for shading). Planning uses adaption pathways with threshold-based decision triggers.
• Redundancy: Planning for crucial capacity duplication (e.g., multiple power feeds, parallel drainage pathways, backup communications) to reduce single points of failure and recovery time. 

• Adaptive management: Continuous monitoring, learning, and adjustment cycles link construction data and early operations to future interventions. Contracts, governance, and budgets should fund monitoring, data ownership, and design upgrades. 
Lifecycle alignment and systems thinking turn climate resilience into measurable KPIs, assured at gates, verified at commissioning, and perpetuated through informed operations (not just a design gesture)[6,7].

5. Review of Climate Resilience Frameworks

## 5.1 Overview of Existing Frameworks

Sendai Framework for Disaster Risk Reduction—UNDRR. Hazard, exposure, and susceptibility cause disaster risk, therefore the Sendai Framework emphasizes prevention, preparedness, and “build back better.” Its national-to-local policy levers, early-warning priorities, and governance principles can inform infrastructure and construction sector guidance. 
AR6 IPCC Adaptation and Resilience Pathways. In AR6, climate impacts, risks, and adaptation alternatives are consolidated to promote risk-informed development and adaptation pathways (time-phased decisions triggered by thresholds). Avoiding maladaptation, mainstreaming equality and inclusion, and evaluating effectiveness across uncertainty ranges are crucial for project acceptance criteria and whole-life decision-making.
World Bank Climate-Smart Infrastructure Framework. CSIF implements climate risk screening and resilience integration across multilateral lender project cycles. It includes hazard screening, economic analysis (benefit–cost of avoided losses), safeguards, and performance indicators. It provides step-by-step checklists and due-diligence expectations for procurement, supervision, and M&E in construction projects[8,9]. 

FIDIC Infrastructure Management Resilience Guidance. FIDIC clarifies responsibilities, risk allocation, information requirements, and lifecycle obligations for owners, engineers, and contractors in contract, design management, and asset management. It enhances standard forms by emphasizing resilience and collaboration under unpredictability. 
Climate Adaptation ISO 14090/14091. ISO 14090 governs climate adaptation in organizations and projects, while ISO 14091 addresses vulnerability, impacts, and risk assessment. They support project management artefacts including charters, risk registers, design bases, and change control by encouraging systematic documentation, traceable assumptions, and iterative review[10].

## 5.2 Application in Project Management Context

Identify and prioritize risks. 
• Translation method: According to Sendai and ISO 14091, climatic risks, exposure pathways, and susceptible functions are identified and fed into the risk register and requirements traceability matrix. The IPCC AR6 emphasis on compounding risks (e.g., heat + power outages) supports scenario sets above single-point estimates.
• Actions taken by PM: Bow ties should include hazard-specific causes and effects, quantify risk reduction from design possibilities, and incorporate no-regrets and low-regrets measures when uncertainty is significant[11].

Flexible scheduling and backup. 
• AR6 adaptation routes guide stage-gated options, prompting design upgrades or operational alterations based on triggers like river level and temperature days. Seasonal/hazard screening by CSIF helps 4D schedules avoid high-risk windows and plan recovery. 
Create weather calendars, resequencing rules, and buffer logic in the baseline program. Define force majeure/data-sharing clauses (FIDIC) to manage monitored thresholds[12]. 
Including stakeholders in resilience planning. 
• Sendai and AR6 emphasize equity, inclusivity, and local knowledge. FIDIC emphasizes owner–engineer–contractor–operators' roles and communications, while CSIF links involvement to safeguards and social performance. 
• PM actions: Map vulnerable user groups, highlight important interdependencies (utilities, emergency services), and include co-benefits (shade, flood amenity) into value narratives for social license[13].

Monitoring and assessing resilience. 
• CSIF and ISO 14090 encourage documentation, indications, and iterative review. AR6 highlights baseline adjustment effectiveness tracking. 
• PM actions: Establish resilience KPIs (e.g., design event downtime, 80% recovery time), commission under stress, and provide digital twins with thresholds for continual decision-making[14].

## 5.3 Comparative Analysis

## Table 1 : Analysis of Key Global Climate Resilience and Adaptation Frameworks and their Applicability in CPM

| Framework | Key Components | Applicability in CPM | Limitations |
| --- | --- | --- | --- |
| UNDRR Sendai Framework | Governance, prevention, preparedness, build-back-better, early warning | Aligns project objectives with national/local DRR policy; strengthens stakeholder engagement and emergency coordination | High-level; requires translation into project-specific tools and KPIs[15] |
| IPCC AR6 Pathways | Risk synthesis, adaptation options, pathways, maladaptation avoidance, equity | Grounds hazard scenarios and adaptive pathways; informs acceptance criteria and trigger points | Not a prescriptive PM guide; needs operationalization in schedules/contracts[16] |
| World Bank CSIF | Screening, economic appraisal of resilience, safeguards, indicators | Clear stepwise integration across project cycle, procurement, supervision, and M&E | Geared to development-bank contexts; may feel heavy for small private projects[17] |
| FIDIC Resilience Guidance | Roles, responsibilities, risk allocation, collaboration, information requirements | Embeds resilience into contract strategy, change control, and data sharing; supports dispute-avoidance | Dependent on contract adoption and client willingness to value outcomes |
| ISO 14090/14091 | Principles of adaptation; VIRA methods; documentation and review | Direct fit with risk registers, design basis reports, and gate reviews; promotes traceability | Requires technical capacity, climate data access, and training to implement[18] |

## 5.4 Emerging Research and Practice Trends

Digitizing climate risk mapping. BIM–GIS overlays evaluate alignments and detail protection systems using flood, heat, wildfire, and wind information. Projects can monitor thresholds (river stage, wet-bulb globe temperature) and automate notifications for schedule rescheduling or temporary activities with digital twins and IoT[19,20].

Scheduling scenarios and adaptive paths. Leading teams encode decision points (e.g., after two 1-in-20-year floods) that unleash design or operational adjustments instead of static baselines. This manages upfront CAPEX and allows for future risk rises.
Natural, low-carbon solutions. The trend is toward nature-based solutions (NBS) such bioswales, living shorelines, and urban shading, which provide cooling, biodiversity, and water quality. Materials and passive design reduce embodied and operational carbon. Synergies (e.g., passive survivability) and trade-offs (durability vs. footprint) are increasingly considered when optimizing the carbon–resilience nexus[21]. 

Resilience KPI standardization. Owners can specify outcome-based specifications and pay for verified performance as research converges on measurable, comparable metrics including service continuity under stress, time-to-recover, and lifecycle cost of avoided losses. 
A policy and science backbone (Sendai, IPCC), process and assurance methods (ISO, CSIF), contractual levers (FIDIC), and digital/technical enablers (BIM–GIS–twins) form a coherent scaffold for construction project management artefacts, gates, and KPIs[22].

6. Policy and Institutional Frameworks

## 6.1 International and Regional Policy Context

Paris Agreement (2015). National Adaptation Plans and adaptation communications require governments to build resilience into infrastructure pipelines, despite the Agreement's mitigation priority. Construction PMs are increasingly expected to screen and disclose upstream resilience in public works and state-backed projects. 
Sendai Framework for DRR (2015–2030). Sendai emphasizes prevention, governance, investment, and preparedness in disaster risk management. This promotes risk-informed land-use, rules, and standards and “build back better.” Sendai enables hazard-inclusive feasibility, emergency coordination plans, and project-close-out post-event learning loops for project teams.
Goals for Sustainable Development. SDGs 9–13 link resilient infrastructure, safe and resilient cities, and climate action. Resilience KPIs (service continuity, time-to-recover) can be bid as outcome metrics for public funders who require SDG mapping[23].

Region-wide efforts. Based on focus: 
• African Union – Climate Resilient Infrastructure Initiative (CRII): Aims to climate-proof transboundary transport, power, and water assets through regional standards, corridor-level risk screening, and blended finance[24].
• The European Green Deal integrates adaptation and climate-proofing into EU funding, taxonomy, and procurement, requiring climate risk assessment and life-cycle perspectives across member states[25].

## 6.2 National and Sectoral Policies

Nigerian National Building Code (2023). Updates improve environmental sustainability and reference performance-based design. Progressive clients are requesting climate risk narratives in design basis studies and including flood/heat factors into siting and drainage requirements. State-level adoption and enforcement vary. 
UK Construction 2025 Strategy and successors. UK policy recommends low-carbon, productive, and resilient delivery, supported by the National Infrastructure Commission and Environment Agency. Planning approval and public procurement increasingly include climate change allowances for flood design, whole-life carbon assessment, and resilience appraisals.
ISC framework for Australia. The ISC rating incorporates resilience, climate risk assessment, and nature-based solutions into design, construction, and operations. State agencies demand ISC/ISCA or comparable ratings on significant works, establishing resilience initiative tender evaluation points and delivery monitoring. 

Sectoral regulators (water, transport, energy) offer asset-specific climate guidance (e.g., riverine flood regulations, heat stress thresholds, wildfire setbacks) that project teams must transform into acceptance criteria and commissioning tests.

## 6.3 Institutional Roles

Government ministries and regulators define norms, planning policies, and fiscal signals (risk-based grant eligibility). Development banks and public financiers (MDBs, DFIs, sovereign funds) require climate screening, economic appraisal of avoided losses, and resilience M&E, defining procurement and monitoring. Engineers' councils and contractors' federations publish practice notes, competency frameworks, and CPD requirements, driving industry adoption. 
Enforcement is patchy, especially in subnational areas with limited inspection resources. Duplication and gaps exist in resilience duties spanning planning, environment, public works, and emergency management. Failure to commission data, monitor results, and share lessons gained hinders knowledge transfer from completed projects to new pipelines.

## 6.4 Policy Gaps and Opportunities

Gaps. 
• Contracts sometimes lack climate risk assessment requirements, discouraging adaptive design or tiered routes.
• Limited tax/financing incentives for durable, low-carbon, and heat-/flood-resilient materials restrict market transition. 

• Standardized KPIs: Lack of common resilience measurements (e.g., permitted downtime) hinders verification and outcome-based remuneration[26]. 
Opportunities. 
• Green and resilience finance: Sovereign green bonds, blended finance, and parametric insurance can reduce project risks and minimize financing costs. 
• Rating and certification systems: Adopting ISC, Envision, CEEQUAL/BREEAM Infrastructure, or RELi links policy goals to auditable project deliverables and continual improvement. 
• Data and digital integration: Open, machine-readable national hazard datasets connected to BIM-GIS standards optimize screening and M&E, promoting equity and market access. 
• FIDIC-style model clauses for data sharing, threshold triggers, and adaptive choices can match owner-contractor incentives with resilience results. 
Overall, clear objectives, verifiable KPIs, and finance-linked incentives can move resilience from a policy ideal into real performance in construction project scopes, schedules, costs, and commissioning[27].

7. Implementation Challenges and Barriers

## 7.1 Technical and Data Limitations

Locally downscaled climatic data for intensity–duration–frequency (IDF) curves, compound flooding, high heat, and wildfire risk is scarce in many studies. Designers extrapolate from previous data despite non-stationarity, mismatching design thresholds and future stressors. Few teams perform multi-hazard stress testing, propagate uncertainty, or calculate avoided-loss benefits for competing solutions. Spreadsheet overlays on BIM models are used to circumvent tooling gaps that prevent mainstream design platforms and codes from integrating climate projections or adaptation pathways. Resilience features can be underspecified, expensive, and hard to commission without consistent data schemas, hazard layers, and verification methods[28].

## 7.2 Institutional and Governance Barriers

Even with high-level promises, climate, planning, public works, and building authorities lack policy coherence. Tender requirements and inspection processes vary due to conflicting or silent norms. Corruption and project mismanagement encourage lowest-first-cost, scope-cutting, and poor materials while avoiding honest risk appraisal. Fragmented requirements imply no single authority owns resilience performance over the asset lifespan, thus monitoring data and lessons learned seldom affect future projects or code upgrades.

## 7.3 Economic and Financial Constraints

While budgets are annual and capital-biased, resilience benefits society over long time and reduces disruption, so project sponsors may view it as cost-inflating. Traditional appraisals undervalue health, productivity, and biodiversity co-benefits and discount potential losses. Municipalities and SMEs have limited access to resilience bonds, concessional/blended finance, and parametric insurance. Without explicit KPIs or payment methods related to verified resilience, contractors struggle to price uncertainty and assume risk for performance-based outcomes.

## 7.4 Human Capacity and Cultural Factors

Many project managers, site supervisors, and estimators have limited experience to adaptation routes, nature-based solutions, or commissioning under stress related to climate risk. Historical design values and deterministic safety considerations dominate professional education, not deep uncertainty or adaptive management. Data gathering, stakeholder involvement, and post-project learning—essential to resilient practice—are challenging to prioritize due to organizational incentives for short-term delivery and milestone compliance.

## 7.5 Case Illustrations (brief)

• Flood-resistant home in Nigeria river basin. A housing project employed bioswales and permeable pavements to improve key services. Building a shared hazard layer with the planning office and agreeing on storm event commissioning tests helped overcome delays caused by missing local IDF curves and uneven municipal drainage regulations.
• Rehabilitating tropical coastal roads. Designers used raised carriageways, breakwaters, and mangrove restoration. Nature-based solutions were hard to appraise alongside concrete infrastructure in procurement. Contractors could propose innovative mixes with tide gauges and incident logs under a hybrid performance clause (maximum closure hours/year)[29].

## 7.6 Summary

## Table 2 : Mitigating Technical, Institutional, Financial, and Human Barriers to Project Resilience

| Challenge Type | Description | Potential Mitigation |
| --- | --- | --- |
| Technical | Sparse local projections; limited multi-hazard modeling; tools not integrating future climates | Invest in open hazard datasets and downscaling; standard BIM–GIS schemas; require stress-test reports at gates; pilot digital twins for threshold monitoring[30] |
| Institutional | Policy fragmentation; inconsistent codes; weak enforcement; corruption risks | Establish cross-sector resilience taskforces; align planning, building, and public-works specs; publish model resilience KPIs; strengthen procurement transparency and audits[31] |
| Financial | High perceived CAPEX; benefits diffuse/long-term; limited instruments | Use whole-life cost and avoided-loss valuation; tie payments to verified outcomes; expand resilience bonds, blended finance, and parametric insurance options[32] |
| Human | Limited climate literacy; short-termism; little post-project learning | Mandatory CPD on climate PM; integrate adaptation pathways into curricula; require lessons-learned and M&E artifacts at close-out; create practitioner communities of practice[33] |

Bottom line: Technical data gaps, fragmented governance, finance frictions, and uneven skills reinforce barriers. Projects that overcome these challenges connect trustworthy hazard data, outcome-based procurement, and adaptive governance to provide, measure, and enhance resilience throughout the asset's life.

8. Pathways for Integrating Climate Resilience into CPM

## 8.1 Embedding Resilience in Project Governance

Resilience Governance Models should include climate goals from inception to handover. List climate hazards and scenarios that impact resilience outcomes (e.g., permissible downtime, recovery time, safe-to-operate criteria) at project charter stage. Bidders must submit a Resilience Integration Plan containing hazard assumptions, design options, seasonal scheduling, monitoring plan, and commissioning under stress. Score bids on outcome-based KPIs, not inputs. Evaluation should consider hazard/scenario justification robustness, adaptive option and trigger point alignment, whole-life value and averted losses, and delivery team competency (training, past performance, supply-chain preparedness). Complete a resilience checklist at each stage-gate (data sources validated, KPIs traceable to design, stress tests conducted, operations triggers established). A Resilience Sponsor on the project board should oversee data, threshold, and change control decisions[34].

## 8.2 Tools and Methods

BIM/GIS climate risk screening. Georeference BIM models and overlay flood, heat, wind, wildfire, and landslide layers in a CDE. Use clash rules and rule-based checks (e.g., minimum freeboard, equipment elevations, egress under inundation) and 4D/5D views to assess seasonal sequences and protection cost implications. 
Resilience-enhancing LCC. LCC should contain expected annual damage/loss (EAD) under changing dangers, downtime costs (service disruption, user delay), and co-benefits. Compare stepwise adaption pathways (do-now/upgrade-later) to major up-front solutions; report avoided loss net present value and flexibility value.
Planning scenarios and adaptive management. River stage, heat degree-days, exceedance frequencies, and preset actions (temporary works, equipment relocation, capacity increases) should be encoded. Cycle through Plan–Do–Check–Act: Do (provide design and procedures), Check (monitor thresholds; commission under stress), Act (invoke pathway actions). Record all triggers and reactions in the risk register and digital twin[35].

## 8.3 Education and Capacity Building

Owners, PMs, designers, and contractors should get foundation (climate literacy, risks), practitioner (scenario/science-to-design translation, NBS, LCC), and advanced (digital twins, outcome-based contracting) training. Project directors, schedulers, and quality/commissioning leads need CPD. Partner with universities and professional bodies to integrate resilience into civil/construction curricula (modules on non-stationarity, adaption pathways, equity, and M&E) and create studio/field laboratories where students apply BIM-GIS hazard overlays and stress testing to real projects[36]

## 8.4 Policy and Financing Innovations

Resilience clauses in PPPs include data-sharing commitments, threshold-based change procedures, and performance incentives connected to confirmed service continuity. Climate-proof materials, nature-based solutions, and proven monitoring systems should get incentives like accelerated depreciation, tax credits, grants, or parametric insurance premium reductions. Document climate risk assessments and resilience KPIs in procurement to qualify for public funding or concessional loans. Use money for adaption features and M&E to foster green/resilience ties. Finally, publish model specifications and KPI catalogs so vendors can innovate against explicit, auditable targets, shifting resilience from discretionary best practice into contracted performance in construction project management[37].

# 9. Discussion

## 9.1 Synthesis of Key Insights

Three trends emerge from the review. International frameworks (Sendai, Paris/SDGs, IPCC pathways) emphasize risk-informed planning, equity, and iterative learning, while practice tools (ISO 14090/14091, CSIF, FIDIC) transform those ideas into procedures, documentation, and responsibilities. Second, integration depends on the project lifecycle: resilience becomes measurable performance when specified in charters, costed in LCC, scheduled with seasonal logic, and confirmed at commissioning. Third, systemic barriers—data scarcity, fragmented governance, cost myopia, and uneven skills—make isolated changes ineffective. Projects require procured, auditable outputs (defined KPIs, contract conditions, payment procedures), but frameworks typically end at principles. Many codes still use historical climatic assumptions, which discourages non-stationary risk adaption and nature-based solutions. Digital enablers (BIM–GIS–twins) can close this gap with trustworthy hazard data and governance (stage-gates, M&E)[38].

## 9.2 Implications for Practice

The path forward for project managers is pragmatic and incremental: 
• Implement risk-based scheduling by incorporating weather calendars, pre-agreed rules, and recovery playbooks into the baseline and testing important activities in extreme circumstances.
• Encourage flexible procurement by requiring a Resilience Integration Plan in bids, evaluating outcome KPIs (e.g., downtime, recovery time), and offering pathway choices with trigger points instead of rigid designs. 

• Develop whole-life value by include predicted annual damage, downtime costs, and co-benefits in LCC. Use NPV of avoided losses to support phased investments. 
• Maintain a georeferenced CDE, overlay hazards in BIM, conduct stress tests, and connect to a digital twin for monitoring and commissioning under stress. 
• Implement knowledge systems: Promote lessons learned and peer exchanges (e.g., contractor forums, owner operator roundtables); update risk registers and acceptance criteria after events. 
• Capability: Assign a Resilience Sponsor to the project board and require CPD for schedulers, estimators, and commissioning leads[39].

## 9.3 Implications for Policy and Research

Enforcement and outcomes should replace guidance in policy. Mandates for climate risk assessments in planning and procurement, standardized resilience KPIs compatible with contracts and inspections, open, machine-readable hazard datasets to level the playing field for SMEs, and finance-linked incentives (grants, tax credits, insurance premium reductions) for verifiable risk reduction are priorities. Regulators can speed adoption by releasing model clauses (data sharing, trigger-based adjustments) and approving nature-based solutions through performance standards rather than checklists.

Comparative empirical evidence should replace conceptual framework in research[40]. Longitudinal studies quantifying resilience investments' cost–benefit and distributional effects, validation of resilience KPIs across asset types, methods for integrating deep uncertainty and adaptive pathways into scheduling and cost control, and effectiveness studies on digital twins and real-time triggers in downtime reduction are needed. A feedback loop is needed to bridge the theory-practice gap: policy sets outcomes, projects deliver and measure, and evidence updates policy and tools, making climate resilience a routine, auditable aspect of construction project management.

# 10. Conclusion

Construction project management must now incorporate climate resilience to build sustainable, reliable infrastructure. With climatic dangers increasing and non-stationarity becoming the norm, resilience must be stated in charters, schedules, and budgets, confirmed at commissioning, and sustained through operations. Frameworks and policies reviewed—from Sendai and Paris architecture to ISO adaptation standards, lender toolkits, and professional guidance—provide a consistent foundation. Fragmented governance, inconsistent data and skills, and procurement mechanisms that prioritize lowest first cost above proven, whole-life performance delay principle-to-practice translation[41].

Closing this gap requires multilevel coordination. Governments should replace advising guidance with enforceable, outcome-based mandates and open hazard data. The industry should operationalize resilience through outcome-focused procurement, BIM–GIS risk integration, and life-cycle cost evaluations that value avoided losses and co-benefits. Academics and professional bodies must integrate climate literacy, adaptive pathways, and performance evaluation into courses and ongoing development while working with owners and contractors to quantify costs, benefits, and equity.

Future building management must shift from efficiency to resilience to handle climatic uncertainties. The sector can move from reactive hardening to proactive, adaptive delivery by aligning policy signals, project governance, digital tools, and financing mechanisms around measurable resilience outcomes, protecting assets and communities and unlocking durable value across the infrastructure lifecycle.

COMPETING INTERESTS DISCLAIMER:

Authors have declared that they have no known competing financial interests OR non-financial interests OR personal relationships that could have appeared to influence the work reported in this paper.

REFERENCES

1. 	Lv Y, Sarker MNI, Firdaus RBR. Disaster resilience in climate-vulnerable community context: Conceptual analysis. Ecological Indicators. 2024 Jan 1;158:111527.

2. 	Schuldt SJ, Nicholson MR, Adams YA, Delorit JD. Weather-Related Construction Delays in a Changing Climate: A Systematic State-of-the-Art Review. Sustainability. 2021 Jan;13(5):2861.

3. 	Macdonald A, McDonald J, Schmitt T, Cai H, Ceponis J, Cullen C, et al. New York State Climate Impacts Assessment Chapter 09: Transportation. Ann N Y Acad Sci. 2024 Dec;1542(1):501–60.

4. 	Majlingova A, Kádár TS. From Risk to Resilience: Integrating Climate Adaptation and Disaster Reduction in the Pursuit of Sustainable Development. Sustainability. 2025 Jan;17(12):5447.

5. 	Torbat Esfahani M, Awolusi I, Hatipkarasulu Y. Heat Stress Prevention in Construction: A Systematic Review and Meta-Analysis of Risk Factors and Control Strategies. Int J Environ Res Public Health. 2024 Dec 17;21(12):1681.

6. 	Gebhard T, Sattler BJ, Gunkel J, Marquard M, Tundis A. Improving the resilience of socio-technical urban critical infrastructures with digital twins: Challenges, concepts, and modeling. Sustainability Analytics and Modeling. 2025 Jan 1;5:100036.

7. 	Setyadi A, Pawirosumarto S, Damaris A. Toward a Resilient and Sustainable Supply Chain: Operational Responses to Global Disruptions in the Post-COVID-19 Era. Sustainability. 2025 Jan;17(13):6167.

8. 	Wamsler C, Johannessen Å. Meeting at the crossroads? Developing national strategies for disaster risk reduction and resilience: Relevance, scope for, and challenges to, integration. International Journal of Disaster Risk Reduction. 2020 May 1;45:101452.

9. 	Travieso Bello AC, Martínez OF, Hernández Aguilar ML, Morales Hernández JC. Comprehensive risk management of hydrometeorological disaster: A participatory approach in the metropolitan area of Puerto Vallarta, Mexico. International Journal of Disaster Risk Reduction. 2023 Mar 1;87:103578.

10. 	Introduction to the FIDIC Suite of Contracts [Internet]. [cited 2025 Oct 14]. Available from: https://globalarbitrationreview.com/guide/the-guide-construction-arbitration-archived/fifth-edition/article/introduction-the-fidic-suite-of-contracts

11. 	Zovko M, Marković Vukadin I, Zovko D. Understanding the IPCC Climate Risk-Centered Framework and Its Applications to Assessing Tourism Resilience. Geographies. 2025 Sep;5(3):45.

12. 	Special Report on Climate Change and Land — IPCC site [Internet]. [cited 2025 Oct 14]. Available from: https://www.ipcc.ch/srccl/

13. 	Al-Sabah RS, Al-enezi SS. Reducing contract disputes: A comparative analysis of FIDIC and GCC standard general conditions of contract for construction projects. Journal of Engineering Research [Internet]. 2024 Oct 16 [cited 2025 Oct 14]; Available from: https://www.sciencedirect.com/science/article/pii/S2307187724002542

14. 	Sixth Assessment Report — IPCC [Internet]. [cited 2025 Oct 14]. Available from: https://www.ipcc.ch/assessment-report/ar6/

15. 	Undrr Work Programme 2024 2025 1 | PDF | Disaster Risk Reduction | Economies [Internet]. [cited 2025 Oct 14]. Available from: https://www.scribd.com/document/694290872/Undrr-Work-Programme-2024-2025-1

16. 	Chapter 7 : Risk management and decision making in relation to sustainable development — Special Report on Climate Change and Land [Internet]. [cited 2025 Oct 14]. Available from: https://www.ipcc.ch/srccl/chapter/chapter-7/

17. 	Operational guidance for monitoring and evaluation (M&E) in climate and disaster resilience-building operations [Internet]. World Bank. [cited 2025 Oct 14]. Available from: https://documents.worldbank.org/en/publication/documents-reports/documentdetail/692091513937457908

18. 	ISO 14090:2019 [Internet]. ISO. [cited 2025 Oct 14]. Available from: https://www.iso.org/standard/68507.html

19. 	Leeonis AN, Ahmed MF, Mokhtar MB, Halder B, Lim CK, Majid NA, et al. Importance of Geographic Information System (GIS) Application to Reduce the Impact of Flood Disasters in Malaysia: A Meta-Analysis. Water. 2025 Jan;17(2):181.

20. 	Olaitan OF, Akatakpo ON, Victor CO, Emejulu CJ, Ayoola TM, Olayiwola DE, et al. Secure and Resilient Industrial IoT Architectures for Smart Manufacturing: A Comprehensive Review. Journal of Engineering Research and Reports. 2025 Jun 21;27(6):331–44.

21. 	Avcı CB, Vanolya M. Proposed Framework for Sustainable Flood Risk-Based Design, Construction and Rehabilitation of Culverts and Bridges Under Climate Change. Water. 2025 Jan;17(11):1663.

22. 	Ilseven E, Puranam P. Measuring organizational resilience as a performance outcome. Journal of Organization Design. 2021;10(3–4):127–37.

23. 	Mogelgaard K, McGray H, Amerasinghe NM. What Does the Paris Agreement Mean for Climate Resilience and Adaptation? 2015 Dec 23 [cited 2025 Oct 14]; Available from: https://www.wri.org/insights/what-does-paris-agreement-mean-climate-resilience-and-adaptation

24. 	The Africa Climate Resilient Infrastructure Summit (ACRIS II) concludes in Addis Ababa | ClimDev-Africa [Internet]. [cited 2025 Oct 14]. Available from: https://www.climdev-africa.org/content/africa-climate-resilient-infrastructure-summit-acris-ii-concludes-addis-ababa

25. 	Vela Almeida D, Kolinjivadi V, Ferrando T, Roy B, Herrera H, Vecchione Gonçalves M, et al. The “Greening” of Empire: The European Green Deal as the EU first agenda. Political Geography. 2023 Aug 1;105:102925.

26. 	Di Febo E. Transition Risk in Climate Change: A Literature Review. Risks. 2025 Apr;13(4):66.

27. 	Gupta S. The Role of Green Bonds in Financing Sustainable Infrastructure Projects: Evidence from Global Markets. Journal of Information Systems Engineering and Management. 2025 Feb 5;10(2):842–51.

28. 	Yan H, Sun N, Chen X, Wigmosta MS. Next-Generation Intensity-Duration-Frequency Curves for Climate-Resilient Infrastructure Design: Advances and Opportunities. Front Water [Internet]. 2020 Dec 3 [cited 2025 Oct 14];2. Available from: https://www.frontiersin.org/journals/water/articles/10.3389/frwa.2020.545051/full

29. 	Echendu AJ. Relationship between urban planning and flooding in Port Harcourt city, Nigeria; insights from planning professionals. Journal of Flood Risk Management. 2021;14(2):e12693.

30. 	Ugliotti FM, Osello A, Daud M, Yilmaz OO. Enhancing Risk Analysis toward a Landscape Digital Twin Framework: A Multi-Hazard Approach in the Context of a Socio-Economic Perspective. Sustainability. 2023 Jan;15(16):12429.

31. 	Islam S. A SYSTEMATIC REVIEW OF PUBLIC BUDGETING STRATEGIES IN DEVELOPING ECONOMIES: TOOLS FOR TRANSPARENT FISCAL GOVERNANCE. American Journal of Advanced Technology and Engineering Solutions. 2025 Apr 29;1(01):602–35.

32. 	Sodje VO, Emmanuel IT, Abdulrasaq HT, Atanda AA, Nwankwo CA, Ifionu ES, et al. Improving Infrastructure Resilience in Developing Regions: Addressing Climate Risks and Natural Disasters in Africa. Journal of Engineering Research and Reports. 2025 Sep 5;27(9):178–93.

33. 	Tshabalala S, Lunga W, Baloyi C. Climate Change Education: Preparing African Youth for Future Challenges. Sustainability. 2025 Jan;17(10):4267.

34. 	Mosadeghrad AM, Isfahani P, Eslambolchi L, Zahmatkesh M, Afshari M. Strategies to strengthen a climate-resilient health system: a scoping review. Globalization and Health. 2023 Aug 28;19(1):62.

35. 	Cao Y, Xu C, Aziz NM, Kamaruzzaman SN. BIM–GIS Integrated Utilization in Urban Disaster Management: The Contributions, Challenges, and Future Directions. Remote Sensing. 2023 Jan;15(5):1331.

36. 	Anyanya D, Paulillo A, Fiorini S, Lettieri P. Evaluating sustainable building assessment systems: a comparative analysis of GBRS and WBLCA. Front Built Environ [Internet]. 2025 Mar 13 [cited 2025 Oct 14];11. Available from: https://www.frontiersin.org/journals/built-environment/articles/10.3389/fbuil.2025.1550733/full

37. 	Sommese F. Nature-Based Solutions to Enhance Urban Resilience in the Climate Change and Post-Pandemic Era: A Taxonomy for the Built Environment. Buildings. 2024 Jul;14(7):2190.

38. 	Mpiere D, Tehami K, Coulibaly I, Mbaiogaou C. Assessing the Integration of the Sendai Framework, Sustainable Development Goals, and the Paris Agreement in Advancing Disaster Risk Reduction and Sustainable Development: Insights from an African Perspective. Journal of Geoscience and Environment Protection. 2025 Jul 31;13(7):350–68.

39. 	Animashaun TA, Sunday O, Ogunleye E, Agbahiwe OK, Afolayan ON, Okpoko OA, et al. AI-Powered Digital Twin Platforms for Next-Generation Structural Health Monitoring: From Concept to Intelligent Decision-Making. Journal of Engineering Research and Reports. 2025 Sep 22;27(10):12–37.

40. 	Shehu H, Sunday O, Ojo DA, Afolayan ON, Adebanjo TA, Eromosele EI, et al. Conceptual Framework for Smart Sensor–driven Predictive Maintenance in Infrastructure Management. Journal of Engineering Research and Reports. 2025 Aug 25;27(9):25–40.

41. 	Enabulele ABO, Omo-Enabulele AP, Borokinni M, Iwerumoh AN, Olatunbosun A, Enobakha BO, et al. Agile Leadership in Hybrid Workplaces: Evolving Roles and Competencies of Project Managers. Journal of Global Economics, Management and Business Research. 2025 Sep 24;17(3):211–25.